## Sheet1
Sprint Backlog for project 4
Sub category | Name/Description | Estimated Time | Completed?
Main control interface | Menu graphics | 1 hour | yes
| Music | 1-2 days | no
Minigame1 (shooty snake) | Improve movement mechanics | 4 hours | yes
| Add lone wolf mechanic | 4 hours | yes
| Fix off screen ball bug | 2 hours | yes (mostly)
| Add levels | 8 hours | yes
| Add points and a leader board | 5 hours | yes
Minigame 2 (pong) | Increasing computer difficulty | 2 hours | yes
| Enhanced 3d graphics | 2 weeks | yes
| Add test code | 3 days | yes
| Add point system | 2 days | yes
Minigame 3 (nim) | Multiple difficullties | 1 day | yes
| Display previous actions | 1 day | yes
| Alter code structure for testing | 1-2 hours | yes
| Test code for game mechanics | 1 day | yes
Documents | User's manual | 1 day | yes
| Deployment plan |  | no
| Maintenance plan | 2-3 days | yes