## Sheet1
Sprint Backlog for project 3
Sub category | Name/Description | Estimated Time | Completed?
Main control interface | Frame and menu | 1 hour | yes
| Link menu to games | 30 minutes | yes
Minigame1 (shooty snake) | shooty snake window | 1 hour | yes
| scheduler for timer | 30 minutes | yes
| initialize game | 2 hours | yes
| game loop functions | 30 minutes | yes
| initial updateModel | 2 hours | yes
| initial renderFrame | 30 minutes | yes
| advanced game logic | 2 hours | yes
| advanced game graphics | 30 minutes | yes
| player logic | 1 hour | yes
| beam-ball collision support | 30 minutes | yes
| player-ball collision support | 2 hours | yes
| win/lose conditions | 1 hour | yes
Minigame 2 (pong) | pong window | 1 hour | yes
| set up game | 1 hour | yes
| game logic | 2 hours | yes
| basic graphics | 2 hours | yes
Minigame 3 (nim) | nim window | 1 hour | yes
| set up game | 1 hour | yes
| game logic | 2 hours | yes
| link to main menu | 30 minutes | yes